## Remaining tasks left
Potential tasks before soft launch on android store and apple store
Priority | Description | Hours needed to add? | Bug fix or an added charge? | Completed | Developer Comment | Tim's Comments | Version tested
High | Ability to be notified that opponent finished their turn while app is closed. |  | Add
High | Ability to close app and return to same game without losing the game. |  | Add
High | If two same factions are picked to fight eachother, have the opposing team highlighted in red outline. |  | Add
High | Monthly crown to top ranked player in the world of the game that is contested every month. If defending champ does not return to defend his title, will go to second ranked player. |  | Add
Low | Change "Strange Matter" text in the game to "Store" |  | Add
Low | Add timer per turn, either five minutes per turn for competitive or a full 24 hours per turn for relaxed gameplay, |  | Add
Low | Reformat the Ability card preview when you hold down on it and it zooms up in the center of the screen to not be so oddly disproportianote |  | Add
Low | Tutorial for beginners |  | Add
Low | Ability to retract minions during setup if you selected them but changed your mind. |  | Add
Low | Add death sounds when minions die and quotes when minions get selected |  | Add
Low | Need a way to decide which player goes first. Eventually it needs to be who has the least experience or rank. but nothing is in place currently. In private lobby, would be nice for maybe a voting system for who to go first, and if it is a split vote, then it goes random. |  | Add
Low | Move setting button to elipsis |  | Add
Low | Ability to see how many players are online |  | Add
Low | Ability to spectate games |  | Add
Low | Chat option within game |  | Add
Low | Preview animation showing an example for what an ability card can do |  | Add
Low | Stats on your profile for games lost and details |  | Add
Low | Have response actions turned to purple and say responcse action |  | Add
Low | I would like as game owner to be able to track what factions are used the most and statistics in the background for trends of players to be able to learn from it. Some sort of tracking system for moves and abilities and ways the game is played. |  | Add
| Hours required: | 0
| Days (8 hour day) required: | 0

## Buggy situation
Buggy situation
Description |  | Hours needed to Fix or Add? | Bug or an added charge? | Fixed | Developer Comments | Tim's comments | Version Tested
| Hours required: | 0
| Days (8 hour day) required: | 0

## Keepers Abilities
Abilities
| Name | Description | Cooldown | Works as intended? | Bug or added charge? | Add | Bug | Bug | Developer Comments | How to repeat bug | Version tested | Comments
1 | Affliction | Your opponent's Guardian loses half of his existing Health Points when you purchase this card | Passive | Yes
2 | Ambush | The next attack by any of your Warriors does not result in a response from the attacked Warrior | 1cc | Yes
3 | Armor | Your Keeper ignores 1 Damage per turn | Passive | Yes
4 | Bounty Hunter | The loot that you collect for each kill is increased by 2 | Passive | Yes
5 | Call to Arms | When the enemy Guardian is Unchained, all your Minions gain +1 Damage | Passive | Yes
6 | Casters | Upon activation of this card, both player's Keepers must activate an available Keeper CC Ability Card without using any other action. The player who activated this card will activate his card first. This effect lasts until the end of the activating players second affected turn. | Passive | Yes
7 | Collapse | Walls deal 1 Damage to enemy attackers when destroyed in addition to any Wall Effect | Passive | Yes
8 | Compromise | Both players' LifeForce and Warriors all gain 3 HP. (HP cannot exceed max HP.) | 2cc | Yes
9 | Comrade | When your Keeper dies and respawns, choose a Minion from the Minion Deck and place him anywhere on your Lifeforce row | Passive | Yes
10 | Critical Hit | When this card is activated, your Keeper attacks once with 3 Damage and 1 Range | 2cc | Yes
11 | Dash | Your Keeper now has +1 Speed | Passive | No |  |  | The Keeper should be able to move 2 spaces (for the direction allowed) for only 1 action point. Currently, the Keeper is completely unchanged while Dash is active. For example, the following grids are different scenarios that represent where the Keeper can move to with 1 action point: For the grids below, the K represents the Keeper, the # represents an empty space, and the X represents the spaces the Keeper can move to. When the Keeper does not have Dash: # # # # # # # X # # # X K X # # # X # # # # # # # When the Keeper has Dash activated. # # X # # # # X # # X X K X X # # X # # # # X # # When the Keeper has Dash and Strafe activated. X # X # X # X X X # X X K X X # X X X # X # X # X |  |  |  | 1.0.23
12 | Deliver | Grants any Warrior within a 1 Space radius of the Keeper an effect which teleports target to its LIfeForce row when attacked instead of receiving Damage. This effect remains on target until used or until the beginning of user's next turn. Teleported Warriors do not receive a response action. | Passive | Yes
13 | Deplete | Your opponent returns 2 Strange Matter to the Economy immediately | 2cc | No |  |  | This card currently does not work at all. |  |  |  | 1.0.23
14 | Explode | When killed, your Keeper deals 3 Damage to everything in a 1 space radius | Passive | Yes
15 | Famine | Neither player can take or use Strange Matter until the end of your second turn after activating this card | 3cc | Yes | [6 empty] | 1.0.18
16 | Forfeit | You must sacrifice a minion for 4 strange matter reserves | 1cc | Yes | [6 empty] | 1.0.18
17 | Ground Pound | When activating this card, your Keeper performs an attack that simultaneously affects everything in a 1 space radius | 1cc | Yes | [6 empty] | 1.0.18
18 | Grounded | On the next attack by your Keeper, he immobilizes the attacked Warrior instead of doing damage. The immobilized Warrior cannot move until it receives damage from a source other than itself | 3cc | No |  |  | When a Keeper with the Grounded ability activated attacks a warrior who is currently grounded already, they become free to move. This shouldn't happen. A keeper with Grounded activated can't do damage to a warrior when attacking them, so the attacked warrior shouldn't be free to move after being hit by a keeper with grounded activated. | Also, when a warrior with the deliver buff on them is attacked by a keeper with grounded activated, the delivered warrior should teleport to the life force row AND be grounded. |  |  | 1.0.18
19 | Health Match | When you activate this card, your opponent must adjust their Keeper's Health Points to match your Keeper's Health Points. | 1cc | Yes | [6 empty] | 1.0.18
20 | Health Slash | Upon activation of this card, cut the enemy Keeper's current Health Points in half. If odd, round up. | 2cc | No |  |  | Currently Health Slash cuts the enemy Keeper's health points by half, then adds 1. This happens when enemy Keeper has even or odd health. For example: When Enemy Keeper has 7 hp. After Health Slash, it goes to 4 hp. When Enemy Keeper has 4 hp. After Health Slash, it goes to 3 hp. When Enemy Keeper has 6 hp. After Health Slash it goes to 4 hp. |  |  |  | 1.0.18
21 | High Stakes | The next attack by any Warrior or Ability will deal 8 damage. Your turn ends upon activation of this card | 3cc | Yes | [6 empty] | 1.0.18
22 | Hinder | Any enemy Warrior within a 1 space radius of your Keeper cannot move from its position | Passive | No |  |  | Enemy Warrior in the radius of Hinder is able to move after the turn in which they break an ice wall. |  |  | Player 1 buys Hinder. Player 2's warrior moves into a 1 space radius from Player 1's Keeper. This will Hinder them. Now Player 2's warrior breaks an ice wall. In Player 2's next turn, they are able to move again within a 1 space radius of the Keeper. | 1.0.18
23 | Hunter | Your Keeper's Damage is doubled when attacking the enemy Guardian | Passive | Yes | [6 empty] | 1.0.18
24 | Hyperdrive | Upon activation of this card, your Keeper can immediately use up to two available CC Ability cards. This card will then be placed on top of the other two used cards in the Activation Field. | 2cc | No |  |  | If Hyperdrive is activated due to the Casters effect, then Hyperdrive's effect is bypassed. |  |  |  | 1.0.14
25 | Immunity | Your Warriors are immune to Wall effects during the turn in which you activate this card | 1cc | No |  |  | Wall Effects still affect friendly warriors during the turn that Immunity is activated. |  |  |  | 1.0.18
26 | Invincible | Your Keeper does not lose Health Points until after the end of your next turn | 3cc | No |  |  | Invincible effect works, but doesn't last long enough. The Keeper that activates this card should be protected for that turn AND their next turn. Basically, the Keeper who activates this card should be invincible for 2 rounds. (One round is when both Players have a turn). Currently the Keeper who activates this card is only invincible for one round. This is what it should be: ROUND ONE: Player 1's Turn: Keeper activates Invincible. <---- Player 1's first turn Player 2's Turn: Invincible is still active for Player 1's Keeper. ROUND TWO: Player 1's Turn: Invincible is still active. <---- Player 1's second turn Player 2's Turn: Invincible is no longer active. Player 2 may now damage Player 1's Keeper. |  |  |  | 1.0.18
27 | Leapfrog | Your Keeper can leap over an occupied space onto an unoccupied space | Passive | No |  |  | Keeper can only jump over warrior and lifeforce cards. Keeper should be able to jump over walls too. | Also, the Keeper should be able to jump over occupied spaces diagonally when Strafe is activated. Currently they cannot jump over any occupied space diagonally. |  |  | 1.0.18
28 | Minefield | Upon activation of this card, the Keeper will place a hidden bomb by positioning markers in all available spaces in a 1 space radius of the Keeper with 1 of those markers representing a bomb. When attacked or moved upon, the bomb will deal 3 damage to everyting in a 1 space radius. Each player may only have 3 bombs on the board at one time. | 1cc | No |  |  | Upon selecting the Minefield ability, the game creates a prompt window that pops up asking if you want to activate that ability card (as it usually does), but after you confirm "yes" when asked to use the ability card, the game then pops up another prompt window asking if you want to use minefield. This results in the player using 2 action points for using the Minefield ability, and leads to bugs if the player tries to use the minefield ability card as their last action. The game should only prompt the player once when they attempt to activate the minefield card. Not twice. |  |  |  | 1.0.18
29 | Minionized | Upon activation of this card, both Keepers have 1 Health Point for the next 3 of the user's turns. If a Keeper dies while under the effect of this card, they will respawn with 1 Health Point. | 2cc | No |  |  | Currently, Keepers under the effect of minionized are able to heal by breaking forest faction walls. This should not happen. Keepers should have a maximum of 1 health point for the next 3 of the user's turn. In other words, Keeper's can't exceed 1 HP during the effect of minionized. |  |  |  | 1.0.18
30 | Mirage | Upon activation of this card, your Keeper switches positions with any of your Warriors. | 3cc | Yes | [6 empty] | 1.0.18
31 | Penalty | The enemy Keeper receives 1 Damage for every space that he moves within his next turn. | 2cc | Yes |  |  | Keepers affected by penanlty should receive damage any time they occupy a new space. This includes teleportation. |  |  |  | 1.0.18
32 | Persevere | Keeper has +1 Damage when below 3 Health Points | Passive | Yes | [6 empty] | 1.0.18
33 | Portal | Place two markers anywhere on the board as portals. These markers are now connected and can be used to travel through. The direction a Warrior enters the portal determines his exit position. For example, if a Warrior moves upward into the portal, he will appear in the space above the portal marker. | Passive | No |  |  | If a keeper under the Penalty ability card effect enters the portal, they die instantly if the distance they cover is large enough. This should not happen. The keeper should only receive as much damage equal to the number of spaces they move when under Penatly. As long as they are only moving 1 space, they should only receive 1 damage. | Also, portal spaces currently act as walls if a warrior is rammed into them (or if a cyborg faction wall pushes a warrior into one). |  |  | 1.0.18
34 | Ram | Keeper may push other Warriors 1 space in the direction of his movement, taking its place. If unable to be moved, the Warrior will receive 1 Damage and neither Warrior will move. Warriors damaged in this way do not receive a response action. | Passive | Yes | [6 empty] | 1.0.18
35 | Range | Keeper has +1 Range | Passive | No |  |  | When Range is active, if a warrior is on a wall, then the Keeper can't attack that warrior (or the wall its on) from 2 spaces away. |  |  |  | 1.0.20
36 | Rebuild | Upon activation of this card, place the original Walls in every available space in the Wall row. | 1cc | Yes | [6 empty] | 1.0.18
37 | Reduction | Upon activation of this card, both players must sacrifice 1 of their Warriors. Loot is taken for each Warrior by the player who sacrificed the Warrior. In the event that both LifeForces have been destroyed, this card may not be played. | 3cc | No |  |  | If Player 1 activates this card for their last action point and sacrifices a minion before Player 2 does, the game gets stuck after Player 2 sacrifices one of their warriors. Neither Player can do anything until Player 1 ends their turn manually. |  |  |  | 1.0.20
38 | Refresh | Upon activation of this card, your Keeper's Health Points increase by 3, up to his maximum Health Points | 2cc | Yes | [6 empty] | 1.0.20
39 | Regeneration | Upon activation of this card, your Keeper gains 1 Health Point. He will also gain a Health Point at the beginning of your next turn. This card cannot cause your Keeper to exceed his maximum Health Points | 2cc | No |  |  | If this card gets activated a second time in the same turn, nothing happens. This is not correct. Each time this card is activated, the Keeper should heal 1 HP. With this being said, The Keeper's next turn is the only turn in which they heal another health point. For example: Player 1's First Turn: Keeper has 1 hp. Keeper activates Regeneration. Keeper heals 1 hp. Keeper activates Reset, and then activates Regneration again. Keeper heals 1 hp. Player 1's Turn ends with Keeper at 3 HP. ... Player 1's Second Turn Keeper is healed 1 hp immediately. Keeper now has 4 HP. Regeneration's effect is finished. Player 1 ends their turn. ... Player 1's Third Turn Keeper is still at 4 HP. |  |  |  | 1.0.20
40 | Repel | When your Keeper attacks a Warrior, that Warrior is pushed 1 space in the direction of the Keeper's attack. If the Warrior cannot move, he receives 1 additional Damage. | Passive | No |  |  | When a Keeper who has this card activated attacks a warrior that cannot move in the direction of the source of the attack, the attacked warrior will repeatedly lose health until death. |  |  |  | 1.0.20
41 | Reset | Upon activation of this card, end cooldown of one of your Keeper's CC Ability Cards immediately and place in your Ability Row. | 2cc | No |  |  | When Reset is activated, the card that the player brings from out of cooldown, that card's effect is cancelled. This should not happen. The card's effect should last as long as the card states, and shouldn't end when brought out of cooldown. |  |  |  | 1.0.20
42 | Resourceful | Your strange matter costs are reduced by 2 until the beginning of your next turn | 2cc | Yes | [6 empty] | 1.0.20
43 | Restore | Upon activation of this card, restore all of your Keeper's Health Points | 3cc | Yes | [6 empty] | 1.0.20
44 | Retaliate | Upon activation of this card, your Keeper will return an equal amount of damage to his attacker until the end of your 3rd turn. Turn count begins in the turn of activation | 3cc | No |  |  | If ram is executed against a Keeper who has this card activated, and the Keeper takes damage from the Ram, then one of the game instances crash. |  |  |  | 1.0.20
45 | Return | Upon activation of this card, both players place all stored Strange Matter into the Economy | 2cc | Yes | [6 empty] | 1.0.20
46 | Revive | Upon activation of this card, resurrect up to 3 Warriors from your Minion Deck that have died during this game | 3cc | Yes | [6 empty] | 1.0.20
47 | Risk | Upon activation of this card, your opponent must reduce their LifeForce by 5 and you must reduce your LifeForce by 10. If this results in simultaneous destruction of both player's LifeForces, both players' Guardians are immediately unleashed and the player whose Keeper is destroyed first loses. | 2cc | Yes | [6 empty] | 1.0.20
48 | Scale | Keeper is able to jump onto or off of walls. If a wall is destroyed below this Keeper, then this Keeper will fall unharmed and unaffected by the wall's effect and will receive a free response. | Passive | No |  |  | If a bomb goes off and destroys a wall which a Keeper is currently on, both the wall and the Keeper receive damage from the bomb. This is not correct. The Keeper should not receive damage from the bomb since the Keeper is on a wall. But the Keeper will receive a response action, since the wall was destroyed underneath them. |  |  |  | 1.0.20
49 | Shockwave | Upon activation of this card, every Warrior and each LifeForce receives 1 Damage per red Ability Card on your Ability Row or in your Activation Field. All loot goes to the Economy. No pieces are allowed responses to this attack. | 2cc | No |  |  | Game crashes for the player who activates Shockwave while Retaliate's effect is activated. |  |  |  | 1.0.20
50 | Slowdown | Upon activation of this card, both players' Warriors can move only 1 space per turn each until the end of the user's 3rd turn following activation | 2cc | No |  |  | The Unchained Guardian is still able to move 2 spaces in one action while Slowdown is in effect. This is not correct. The Guardian should be limited to only being able to move 1 space just like the rest of the warriors. |  |  |  | 1.0.20
51 | Snipe | Upon activation of this card, your Keeper attacks with 1 Damage and up to 3 Range | 1cc | No |  |  | Currently, when this card is activated, the Keeper has 3 range and 1 damage for the remainder of their turn. This is not correct. The Keeper should immediately make an attack with 3 range and 1 damage upon activation of this card. (like how Critical Hit should function). |  |  |  | 1.0.20
52 | Sprint | Upon activation of this card, a Warrior of your choice will have a +3 Speed for 1 action during this turn | 3cc | No |  |  | If Sprint is activated and a warrior is chosen to have the effect, but the player then moves any other warrior before moving the chosen warrior, then the chosen warrior will no longer have +3 speed. What should happen is that the chosen warior should have +3 speed until that warrior spends an action moving in the turn the card is activated. | Also, +3 speed means to add 3 to the number of spaces that warrior can already move. Meaning, if a warrior with 2 speed is chosen when Sprint is activated, then that warrior will be able to move 5 spaces with one action. |  |  | 1.0.20
53 | Steadfast | Upon activation of this card, enemy Minions cannot hurt your Keeper until he moves or is moved from his position. Any attacks on your Keeper will still result in a response from the Keeper as normal. | 2cc | No |  |  | Currently, when a Keeper with Steadfast active uses Mirage to teleport to one of their minions, they still won't receive damage from enemy minions until moving. This is not correct. Mirage should deactivate Steadfast's effect. This is because telporting is still counted as moving. |  |  |  | 1.0.20
54 | Stealth | Keeper may mask his movement by placing markers in available movement spaces, including his current location, with a unique marker indicating his new location. Attacking, Enemey Vision, attempting to move onto the Keeper, or subsequent movement by the Keeper will reveal the Keeper. If an enemy Warrior attempts to move onto the Keeper, the Warrior stay on his original space and the Keeper receives a response action. | Passive | Yes | [6 empty] | 1.0.20
55 | Strafe | Keeper can move and attack diagonally | Passive | No |  |  | If a Keeper has this passive card as well as Dash, the Keeper should be able to move to a space that is two spaces away diagonally with one action point. Currently they cannot. For example For the grids below, the K represents the Keeper, the # represents an empty space, and the X represents the spaces the Keeper can land When the Keeper only has Strafe activated: # # # # # # X X X # # X K X # # X X X # # # # # # When the Keeper has both Strafe and Dash activated. X # X # X # X X X # X X K X X # X X X # X # X # X |  |  |  | 1.0.18
56 | Strength | Keeper has +1 Damage | Passive | No |  |  | Currently does not glow when purchased but should glow all the time as it is passive |  |  |  | 1.0.18
57 | Stun | Your Keeper may use an action to immobilize an enemy Warrior within a Range of 2 until the beginning of your next turn. Immobilized units can use any other actions other than movement including attacking, responding, and abilities. | Passive | No |  |  | Ram should not damage an immobilized warrior. Ram can still be used to move an immobilized warrior in the direction of the ram user's movement. The purpose of Stun is to keep the affected warrior from spending an action point to move, it does not prevent the warrior from being able to be moved. |  |  |  | 1.0.18
58 | Subdued | Neither player can activate or reactivate a CC Ability Card until a Keeper dies | 2cc | Yes | [6 empty] | 1.0.20
59 | Tar | Upon activation of this card, immobilize enemy Guardian for the next 2 of your opponent's turns | 2cc | No |  |  | After activation, if the enemy Guardian breaks an Ice Faction Wall, then it will be able to move in the following turn before it should. |  |  |  | 1.0.20
60 | Tax | Choose one of your opponent's Keeper's CC Ability Cards to permanently cost 1 Strange Matter per use of that ability as payment to you. | Passive | No |  |  | The intended behavior of Tax is to make one of the enemy's ability cards cost 1 strange matter to use for the rest of the game. After you choose an opponent's ability card to tax, the opponent will need to pay you 1 strange matter to use it. It should cost 1 strange matter for the opponent. If the opponent doesn't have enough strange matter, they can't use that taxed card. |  |  |  | 1.0.20
61 | Teleport | Upon activation of this card, your Keeper will teleport to any space adjacent to your LifeForce | 1cc | No |  |  | If every space adjacent to the lifeforce is occupied, then any space adjacent to those is available, and so on. For example: (L = Lifeforce, # = occupied, X = available) X X X X X X # # # X X # L # X If there is no unoccupied space on the board, Keeper receives 1 damage. |  |  |  | 1.0.20
62 | Toughen | Keeper has a maximum of 7 Health Points. Keeper's Health Points are replenished to 7 upon initial purchase of this card. | Passive | Yes | [6 empty] | 1.0.20
63 | Truce | Upon activating this card, no damage can be dealt or received by either players until the end of your 3rd turn | 2cc | No |  |  | Players should still have the option to spend an action to attempt to deal damage, even if no damage can be dealt. Don't restrict players from making attempts to attack. |  |  |  | 1.0.20
64 | Veto | Upon purchasing this card, you must choose one of your opponent's Ability Cards (either from their hand or purchased) to be placed and turned perpendicular in the ability row and remain unusable for the remainder of the game along with this card. | Passive | No |  |  | Veto functions perfectly, this bug concerns the Graphical User Interface. If the player vetos an enemy ability card which is currently in the activation field, then that ability card should be forced to be placed back into the enemy's ability row turned perpendicular the moment it is vetoed. |  |  |  | 1.0.20
65 | Vision | Keeper reveals all hidden enemy markers within a 1 space radius | Passive | No |  |  | Hidden Bomb cards should not explode when revealed by Vision. Also, when a warrior in stealth is revelealed by Vision, they do not get a response action. Response actions are only given to warriors who are revealed due to another warrior attempting to move on to their space. |  |  |  | 1.0.20
66 | Void | Upon activation of this card, place a blank marker on any open space. This will now act as an immediate death space, killing any Warrior that moves or is moved onto it. Ignore any other protective abilities. | Passive | No |  |  | Deliver should not protect warriors from this Void space. Void will disregard all other protective abilities and kill any warrior which lands on it. |  |  |  | 1.0.20
67 | Vulnerable | Enemy Keeper respawns with only half of his maximum Health Points after death. If odd, round up. | Passive | Yes | [6 empty] | 1.0.20
68 | Wall Builder | Upon activation of this card, place a Wall in any open space | 2cc | No |  |  | The game runs out of wall cards for each faction after 10 walls. |  |  |  | 1.0.20
69 | Weaken | Enemy Guardian now only deals 2 Damage | Passive | Yes | [6 empty] | 1.0.20
70 | Wounded Runner | When Keeper is at 1 Health Point, he will also have 3 speed | Passive | No |  |  | The keeper should not be able to move with 3 speed if there health is above 1. Currently, if the Keeper has 1 health and gets healed, the Keeper will still be able to move with 3 speed until they move. This is not correct. The moment the Keeper's health is above 1 hp, their movement is no longer being effected by Wounded Runner. |  |  |  | 1.0.20
[10 empty] | Do not work as intended |  | Work as intended
[10 empty] | 36 |  | 34
Note on C23: User's turn ends upon activation. The next attack by any Warrior or Ability will deal 8 damage regardless of any active modifiers. -Sam Turner
Note on C31: Possible description change for clarity: For the next 3 of the user's turns, both Keepers have a maximum of 1 Health Point. This effect persists through death. -Sam Turner
Note on C33: The enemy Keeper receives 1 Damage for every new space they occupy during their next turn. -Sam Turner
Note on C53: Causes the Keeper to immediately make an attack with 3 Range and 1 Damage. -Sam Turner
Note on C55: Your Keeper will no longer receive damage from enemy Minions until your Keeper occupies a new space. Your Keeper still receives response actions as usual. -Sam Turner
Note on C62: Upon purchase, choose one of your opponent's purchased CC Ability Cards to permanently cost 1 strange matter to activate as payment to you. -Sam Turner
Note on B63: Home Warp Life Warp Home Bound Homecoming Retreat -Sam Turner
Note on C63: Keeper teleports to any space adjacent their Lifeforce. If these spaces are occupied, then any space adjacent those spaces. If every space on the board is occupied, Keeper receives 1 damage. -Sam Turner
Note on C66: Upon purchase, render any one of your opponent's ability cards permanently unusable. Unusable cards are rotated perpendicular to the board. -Sam Turner

## Factions and Ultimates
Factions and Ultimates
Name | Description | Hours needed to fix or add? | Work as intended | Add | Bug | Bug | Bug | Bug | Developer Comments | Version tested | Comments | Additional comments
Cyborg warriors |  |  | Yes
Cyborg Ultimate: Command | Take command of any enemy Warrior within a 1 space radius for the remainder of the turn. This ability is usable only once per game. |  | Yes
Cyborg wall: |  |  | Yes
Dragon warriors |  |  | Yes
Dragon Ultimate:Resurrect | Player is able to bring back any one of their dead minions from graveyard to appear adjacent to his Lifeforce and be available on the next turn. Usable once per game. |  | Yes
Dragon wall: | Destroying this wall will deal damage of one HP to any warrior in a one space radius. This does not destroy other walls. |  | Yes
Forest warriors |  |  | Yes
Forest Ultimate:Regrowth | Upon use, the Keeper adds 2 HP to themselves. This ability is only once per game. |  | Yes
Forest wall: | When adjacent to the attacker, this destroyed wall will give 1 HP to the attacker. Not to exceed maximum health. |  | Yes
Snow warriors |  |  | Yes
Snow Ultimate: Freeze | Restrict all enemy Warrior's movement actions until the beginning of your next turn. This Ability is usable only once per game. |  | Yes
Snow wall: |  |  | Yes
| Hours Required: | 0
| Days (8 hour day) Required: | 0

## Warriors and Features of Game
Warriors and Features
Name | Work as Intended? | Hours needed to fix or add? | Bug or added charge? | Add | Bug | Bug | Bug | Bug | Developer Comments | Version tested | Comments | Replicate bug
Keeper | No |  |  |  | Player 2 Keeper's is not able to allow minions to move for the response action or ability and has a prompt that comes up. Player 1 Keeper is working correctly |  |  |  |  | 1.0.23
Ogre | Yes
Mage | Yes
Sniper | Yes
Bomber | Yes
Blockader | Yes
Scaler | No |  |  |  |  | If a scaler is standing on a wall and a bomb explodes next to the wall the scaler is standing on, after the scaler falls unharmed to the ground level, the scaler should get a free response. Currently this does not happen. |  |  |  | 1.023
Scout | Yes
Chained Guardian | Yes
Unchained Guardian | Yes
Strange Matter | Yes
Economy | Yes
Ability Cards | No |  |  |  | Currently, whenever an ability card is brought back from activation field, its effect is immediately reset. This should not happen, an ability card's effect should last for as long as the ability's description dictates. (Keep in mind, CC effects do not overlap. The rulebook describes this: "There cannot be an overlap of duplicate CC effects. If a card has been reactivated before its previous effect has ended, it will not cause a duplicate effect and instead will have no effect") | Need the cards stretched out to normal format such as the wall cards or Keeper cards are when you hold down on them to look at them closely |  |  | I cloudn't replicate, here is example of using Famine: https://streamable.com/hwa9ws If you found card that is not following this rule please let me know | 1.0.18 |  | Activate Ambush, then any other cc card to so that Ambush can be brought back from the Activation Field in the same turn. At this point Ambush has been reset, so if the Player who activated Ambush attacks an enemy warrior, the game breaks with both players seeing different game notification messages.
Shared Hand | Yes
CC Cooldown Cards | Yes
Passive Cards | Yes
Walls | No |  |  |  | Ranged attacks should not destroy a wall such as snipe. |  |  |  |  | 1.0.23
Bombs | No |  |  |  | Currently empty markers stay when a bomb explodes. If bomb explodes, the other markers that were generated with that bomb should disappear. Only markers that should ever stay are ones generated by another bomb or warrior who is still in hiding. Once that bomb or warrior are either revealed or destroyed, the associated markers should leave. |  |  |  |  | 1.0.23
Markers | Yes
Attacking | Yes
Attacking from a Wall | Yes
Moving | Yes
Switch Places with Friendly Warrior | Yes
Menu Options | Yes
Menu music | Yes
Warrior quotes | Yes
Oppoent card interaction | Yes
Icons | Yes
Private Match | Yes
Random match | Yes
Activation field | Yes
Background | Yes
About page | Yes
Faction selection page | Yes
Turn change | No |  |  | Add a sound for when a player's turn has ended.
Loot reward chart | Yes
Credits | Yes
Minion cards | No |  |  |  | For unknown reasons, minion cards will become horizontal when you hold down on them to look at them more closely |  |  |  |  | 1.0.23
Minions | Yes
Log in | No |  |  |  | Fake emails can create accounts | Closing game completely causes loss of memory of game so that when player signs back in, they cannot rejoin the game they were playing. This will be a serious issue if battery of phone is lost in middle of game. Players should be able to completely logout or close app and sign back in or reopen and automatically rejoin same game |  |  |  | 1.0.23
Profile | No |  |  |  | Players need to see their username displayed on main menu, should be able to access details about profile in settings, and be able to see their profile in the settings within game as well as name of opponent |  |  |  |  | 1.0.23
Android Version | No |  |  |  | Android version seems laggy |  |  |  |  | 1.0.23
IOS Version | Yes
0
0

## Sound effects
Sound effects
Name | Voice Actor | Trigger | Sound | Chance this would happen when triggered | Leveled out MP3 for developer | Works as intended? | Hours needed to fix or add? | Add | Bug | Bug | Developer Comments | Version tested | Comments | Additional comments
Ability card purchased | *Sound effect* | When any ability card is purchased |  | Always |  | Yes
Ability card used | *Sound effect* | When any ability card is used |  | Always |  | Yes
Attack sound | *Sound effect* | Any attack |  | Always |  | Yes
Background music | *track provided* | When in game | *provided mp3* | Always | Link | Yes
Bomb exploding | *Sound effect* | When bomb is destroyed | *bomb exploding* | Always |  | Yes
Cyborg Blockader | Ken | When using Ram | "Don't mind me" says as grunting | Always | Quote | Yes
Cyborg Blockader | Ken | When moving | "Yes, good plan," "I am ready," "My shield will protect me" | Always | Quote 1, Quote 2, Quote 3 | Yes
Cyborg Bomber | *Sound effect* | When using minefield | *bury sound* | Always |  | Yes
Cyborg Bomber | *Sound effect* | When moving | *robot walking sound* | Always |  | Yes
Cyborg Chained Guardian | *Sound effect* | When moving | *loud metal clank* | Always |  | Yes
Cyborg Mage | Suzi | When using deliver | "If you are hurt, I will help you." | Always | Quote | Yes
Cyborg Mage | Suzi | When using stun | "Do not move a limb" | Always | Quote | Yes
Cyborg Mage | Suzi | When moving | "Yes." , "As the Keeper commands.", "I am in search of the needy." | Always | Quote 1, Quote 2, Quote 3 | Yes
Cyborg Ogre | Titus | When groundpound is used. | "All around me, pain!!" | Always | Quote | Yes
Cyborg Ogre | Titus | When moving | "I cannot wait to devour my foe!", "The iron is hot, let us strike!", "I will demolish!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Cyborg Scaler | *sound effect* |  |  | Always |  | Yes
Cyborg Scout | Brad | When Moving | "This area is safe, for now", "My vision is clear", "As you wish" | Always | Quote 1, Quote 2, Quote 3 | Yes
Cyborg Sniper | Josh | When going into Stealth | "They will not see me coming" | Always | Quote | Yes
Cyborg Sniper | Josh | When moving | "My aim will be true" , "With my bow, I shall pursue", "Yes, with purpose" | Always | Quote 1, Quote 2, Quote 3 | Yes
Cyborg Unchained Guardian | *Sound effect* | When moving | *loud metal clank* | Always |  | Yes
Cyborg Wall | *Sound effect* | When destroyed |  | Always |  | Yes
Dragon Blockader | Bill | When using Ram | "You appear to be in my way!" | Always | Quote | Yes
Dragon Blockader | Bill | When moving | "Come at me! I am ready!", "Would you like to be a prisoner of my rage?", "I eat rocks for filler food." | Always | Quote 1, Quote 2, Quote 3 | Yes
Dragon Bomber | Sam | When using minefield | "Mind your step" | Always | Quote | Yes
Dragon Bomber | Sam | When moving | "laughs, lets go!", "Let's get this party started!", "Gifts to share, come get them!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Dragon Chained Guardian | *Sound effect* | When moving | *water splash sound* | Always |  | yes
Dragon Mage | Titus | When using Stun | "Perhaps, you move no more." | Always | Quote | Yes
Dragon Mage | Titus | When using Deliver | "If in danger, may you be delivered." | Always | Quote | Yes
Dragon Mage | Titus | When moving | "I will not second guess you, Keeper", "No danger will slow my cause!", "Always ready, always mindful." | Always | Quote 1, Quote 2, Quote 3 | Yes
Dragon Ogre | Tim | When groundpound is used. | "Feel the ground shake beneath you!" | Always | Quote | Yes
Dragon Ogre | Tim | When moving | "If I must", "I can see the fear in their eyes!", "A few more steps, and their days are over" | Always | Quote 1, Quote 2, Quote 3 | Yes
Dragon Scaler | Wesley | When moving | "As you wish my liege", "Please, give me a challenge", "Our foes will scatter as your plan becomes clear!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Dragon Scout | Sally | When moving | "Yes, I will take this spot.", "I have spotted something in the distance", "May your Lifeforce live on forever!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Dragon Snper | Tim | When going into Stealth | "I will fly into the clouds, and like lightning appear." | Always | Quote | Yes
Dragon Snper | Tim | When moving | "Cold. But so is war", "We will hit them hard, we will hit them fast.", "I have no concerns." | Always | Quote 1, Quote 2, Quote 3 | Yes
Dragon Unchained Guardian | *Sound effect* | When moving | *slithering* | Always |  | Yes
Dragon Wall | *Sound effect* | When destroyed | *fire crackle sound* | Always |  | Yes
Forest Blockader | Sam | When using Ram | "I asked nicely, now out of my way!" | Always | Quote | Yes
Forest Blockader | Sam | When moving | "Why can't I be the Guardian", "Hmm, it seems this way. Very well." , "Keeper, I need more battle!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Forest Bomber | Doug | When using minefield | "I have set the trap! Now we wait for the bang!" | Always | Quote | Yes
Forest Bomber | Doug | When Moving | "Tried and true are the ways of my bombs!", "If you hear ticking, that would be me.", "Let me know when you need me to blow something up!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Forest Chained Guardian | *Sound effect* | When moving | *Rustling of leaves* | Always |  | Yes
Forest Mage | Katie | When using deliver | "I offer you my protection!" | Always | Quote | Yes
Forest Mage | Katie | When using stun | "I will hold them here!" | Always | Quote | Yes
Forest Mage | Katie | When moving | "If peace cannot be found, then so be it.", "Yes, my powers are ready at your command." , "They are coming. Let us be ready." | Always | Quote 1, Quote 2, Quote 3 | Yes
Forest Ogre | Levi | When groundpound is used. | "Feel the quake of my paws!" | Always | Quote | Yes
Forest Ogre | Levi | When moving | "Looking forward to an altercation", "Yes, of course, just don't keep me from the fighting", "I smell fear." | Always | Quote 1, Quote 2, Quote 3 | Yes
Forest Scaler | Sam | When moving | "I will climb any wall I find", "Agile, yes, I am.", "I sense villainy." | Always | Quote 1, Quote 2, Quote 3 | Yes
Forest Scout | Simon | When moving | "I see the enemy as well as their plan", "Of course, this is the correct way" , "May the forest reign forever" | Always | Quote 1, Quote 2, Quote 3 | Yes
Forest Snper | Tapi | When going into Stealth | "Still and calm with only my arrow to break the silence." | Always | Quote | Yes
Forest Snper | Tapi | When moving | "May your wisdom guide me", "Yes, Keeper, you would know best", "Let them dare step up!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Forest Unchained Guardian | *Sound effect* | When moving | *Branches breaking* | Always |  | Yes
Forest Wall | *Sound effect* | When destroyed |  | Always |  | Yes
Menu Music | *track provided* | When not in game | *provided mp3* | Always | link | Yes
Snow Blockader | Stefan | When moving | "I will take my stand here", "May none be in my way," , "Of course, you are the Keeper" | Always | Quote 1, Quote 2, Quote 3 | Yes
Snow Blockader | Stefan | When using Ram | "Out of my way!" | Always | Quote | Yes
Snow Bomber | Adam | When using minefield | "This is what I live for!" | Always | Quote | Yes
Snow Bomber | Adam | When moving | "If you say so", "Yes, but note that I need to blow something up soon please", "Look out for my bombs!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Snow Guardian Chained | Sam | When moving | "grunts" | Randomly alternate but there is always a sound when Chained guardian moves | Quote 1, Quote 2, Quote 3 | Yes
Snow Guardian Unchained | Sam | When moving | "heavy breathing grunting" | Always | Quote | Yes
Snow Mage | Tony | When using Stun | "You have moved enough for one turn." | Always | Quote | Yes
Snow Mage | Tony | When using Deliver | "You will be protected." | Always | Quote | Yes
Snow Mage | Tony | When moving | "If you say so.", "I fear only our loss.", "I shall bring along my enchantments." | Always | Quote 1, Quote 2, Quote 3 | Yes
Snow Ogre | Titus | When groundpound is used. | "Pain is coming" | Always | Quote | Yes
Snow Ogre | Titus | When moving | "I fear nothing.", "The cold is my ally." , "I welcome a fight." | Always | Quote 1, Quote 2, Quote 3 | Yes
Snow Scaler | Sam | When moving | "I am no bug, but I will bug you!", "I will bury them beneath the ice!", "No wall can hinder me!" | Always | Quote 1, Quote 2, Quote 3 | Yes
Snow Scout | Ken | When moving | "You are the Keeper", "No foe has best me yet", "I will scout ahead." | Always | Quote 1, Quote 2, Quote 3 | Yes
Snow Snper | Lili | When using stealth | "I shall make myself small." | Always | Quote | Yes
Snow Snper | Lili | When moving | "Yes master" , "As you wish" , "I shall do so quietly" | Always | Quote 1, Quote 2, Quote 3 | Yes
Snow Wall | *Sound effect* | When destroyed | *ice shattering* | Always |  | Yes
Strange Matter | *Sound effect* | When collected | coin sound
[6 empty] | Hours required: | 0
0
[13 empty] | Work as intended | Do not work as intended
[13 empty] | 68 | 0

## Credits
Credits and Special Thanks
App Developer:
Maverick Masterminds LLC
MagmaDev
Illustration Artists:
Milos Zecevic
Jonah Greene
Jose Lopez
Graphic Design:
Joseph Fox
Sam Turner
Tim Turner II
MagmaDev
Menu Music:
Corbin Wescott
Background Music:
Tim Turner II
Corbin Wescott
Tapian Turner
Game concept and design:
Tim Turner II
Voice Actors:
Sam Turner
Wesley McCullough
Levi Sisko
Titus Turner
Tony Payne
Simon J. Peters
Douglas Cloven
Adam Parsons
Katie Turner
Lili Turner
Sally Turner
Tim Turner II
Tapian Gibson
Ken Bartels
Suzi Bartels
Stefan Hinkley
Brad Reynoso
Josh H.
MC Clendon
Special Thanks:
Sam Turner
Liliana Turner
Tapian Turner
Joseph Fox
Adam Parsons
Milos Zecevic
Bryan Riester
EndyMinionGames
Mustache Power
Gnork Games
Titus Turner
Jonah Greene
Jose Lopez
Ruth Ashton
Steve Ellis
Kerry Kuenzi
Levi Sisko
Wild Things Gaming
Borderlands

## Iphone and Android Bugs
Device | Bug | Version tested